## Fit-Gap Matrix
Project Objective / Area | Requirement | Known Current State (source-based) | Target State / Acceptance Criterion | Fit-Gap Status | Atoti Fit (to be confirmed) | Priority | Next Step / Evidence | Question for ActiveViam
KR1 – Sensitivities | Identify and document all SIMM-relevant sensitivities | Calypso runs daily Risk Analysis Scheduled Tasks for sensitivities; CRIF/scenario files are used in the existing process. | Sensitivity catalogue covering SIMM Risk Type, Risk Class, source, calculation, mapping and validation | Partially known – details to be completed | Open – to be confirmed by ActiveViam | Must-have (provisional) | Calypso sensitivity documentation; ActiveViam demo | Which SIMM Risk Types and Risk Classes are supported? Which CRIF fields/formats are expected?
KR1 – FRTB Synergies | Assess overlaps and gaps between FRTB and SIMM sensitivities | The project objective requires an analysis; the available information does not evidence a complete mapping matrix. | Mapping for each sensitivity, including unit, tenor/grid, sign, aggregation and required transformation | Open – analysis required | Offen – fachlich/technisch prüfen | Must-have (provisional) | Compare the FRTB sensitivity inventory with the SIMM catalogue | Can existing FRTB data be used directly, or are SIMM-specific calculations/transformations required?
KR1 – Trade Filters | Document existing trade filters and map them for implementation in Atoti | The project objective requires existing filters to be analysed; the complete filter rules are not yet documented here. | Documented inclusion/exclusion rules covering product scope, status, legal entity and exceptions | Open – analysis required | Open – to be confirmed by ActiveViam | Must-have (provisional) | Review Calypso configuration and the daily process chain | Where are filters applied: before sensitivity calculation, during CRIF import, or before SIMM aggregation?
KR1 – IM Netting Set Assignment | Assign trades correctly to an IM CSA/netting set | The Calypso documentation identifies the Colline_IM_AgreementID attribute. A daily report checks for missing assignments for EBVI and LINZ_SPK; subsidiaries perform local checks. | Unambiguous assignment logic, source of reference data, history tracking and error handling | Teilweise known – Prozessdetails to be completed | Open – to be confirmed by ActiveViam | Showstopper if correct assignment is not possible (provisional) | Document Calypso/Colline assignment and monitoring | Can Atoti manage the assignment, or must it be supplied by Calypso/Colline? How are missing/ambiguous assignments detected?
KR2 – Risk Management Reporting | Reporting and data analysis for Risk Management | The project objective requires these needs to be analysed and documented; detailed requirements still need to be gathered. | SIMM results with drill-down by Risk Class/Type, portfolio/trade; time comparisons, plausibility checks and exports as required | Open – stakeholder workshop required | Offen – ActiveViam-Demo | Must-have (provisional) | Gather requirements with Risk Management | Which drill-down levels, filters, exports and daily comparison options are available out of the box?
KR2 – Collateral Management | Reporting and data analysis for Collateral Management | The existing process transfers SIMM results to Colline; missing IM CSA assignments are reported. | IM by counterparty/CSA and pay/receive side, reconciliation with Colline, discrepancy and completeness checks | Teilweise known – Anforderungen zu erheben | Offen – ActiveViam-Demo | Must-have (provisional) | Involve Collateral Management; define reconciliation with Colline | Which reconciliation, export and exception-management features does the solution provide?
KR2 – Front Office / Pre-trade | Reporting, analysis and pre-trade SIMM calculation | Pre-trade SIMM is explicitly included in the project objective; its current implementation status in Atoti is not evidenced. | Add a hypothetical trade, calculate incremental IM and compare multiple scenarios without changing production data | Open – business requirements to be clarified | Offen – gezielte Demo erforderlich | Classify as Must-have or Nice-to-have based on target state | Front Office workshop; demo using an example trade | Does Atoti support hypothetical trades and ΔIM? How are sensitivities for new trades generated and validated?
KR3 – Atoti Feature Inventory | Analyse the current Atoti feature list | The project objective requires reviewing the current feature list; the list itself was not available in the information reviewed here. | Feature inventory with evidence, limitations, licensing/configuration dependencies and demo evidence | Open – feature list required | Open – to be confirmed by ActiveViam | Must-have to complete the fit-gap assessment | Obtain the feature list from ActiveViam and map it against requirements | Which features are available in production, configuration-dependent, on the roadmap, or customer-specific?
KR3 – SIMM Methodology & Version | Correctly support the SIMM methodology, version and relevant risk classes | The Calypso guide describes the SIMM methodology; the target version and Atoti feature scope still need to be confirmed. | Evidence of SIMM version, Delta/Vega/Curvature and relevant risk classes; reproducible results | Open – target version to be defined | Open – to be confirmed by ActiveViam | Showstopper if required regulatory coverage is missing (provisional) | Define the target version and validation approach | Which SIMM version is supported? How are version changes, regression tests and independent validation handled?
KR3 – Data Integration / CRIF | Reliably load and validate sensitivities/CRIF and reference data | In the current Calypso process, sensitivities are calculated and files exported; the target Atoti architecture still needs to be confirmed. | Defined interface, data quality checks, completeness controls, error logging and restart/recovery | Partially known – target integration open | Open – to be confirmed by ActiveViam | Must-have (provisional) | Document the data flow Calypso → Atoti → reporting | Which interfaces/formats are supported? How are missing, duplicate or late data handled?
KR3 – Reconciliation / Validation | Validate Atoti results against existing/official SIMM results | The Calypso process generates SIMM results for the existing workflow; the target reconciliation with Atoti still needs to be defined. | Comparison at netting-set and total level, tolerances, root-cause analysis and documented sign-off | Open – validation plan required | Open – to be confirmed by ActiveViam | Showstopper for production go-live if robust validation is not possible (provisional) | Define reference portfolios and acceptance criteria | What result granularity is available? How can differences be traced back to sensitivity/trade level?
KR3 – History / Attribution | Analyse historical results and changes | Specific requirements and current Atoti functionality are not evidenced. | Historical snapshots, day-on-day comparison and, where possible, explanation of IM changes | Open – stakeholder needs to be clarified | Open – to be confirmed by ActiveViam | Must-have or Nice-to-have depending on requirements | Consult Risk Management and Collateral Management | How long are results retained? Are day-on-day comparisons and attribution by risk/trade available?
KR3 – Performance / Operations | Ensure calculation runtime, data volume capacity and operational readiness | Not evidenced by the available sources. | Demonstrated performance for relevant portfolios, SLA, monitoring and error handling | Open – not assessed | Open – to be confirmed by ActiveViam | Must-have before production use | Gather volume, runtime and operational requirements | What benchmarks are available? How are calculation runs monitored and rerun?

## Legende
Begriff | Definition
Status | Bedeutung
Fit bestätigt | Anforderung nachgewiesen erfüllt; Nachweis/Demo/Tests dokumentieren.
Partially known – details to be completed | Ein Teil des Ist-Prozesses ist dokumentiert, aber die Anforderung ist noch nicht vollständig abgedeckt.
Open – analysis required | Ist-Prozess oder Anforderung muss intern erhoben werden.
Open – to be confirmed by ActiveViam | Keine belastbare Aussage zur Produktfunktion; Demo oder schriftliche Bestätigung erforderlich.
Gap bestätigt | Anforderung ist nachweislich nicht erfüllt; Lösung/Workaround und Auswirkung dokumentieren.
Priority | Alle Prioritäten sind provisionale Vorschläge und müssen mit Stakeholdern bestätigt werden.